## Sheet1
Level 1 | Level 2 | Level 3 | Level 4 | Level 5
Baggage handling system | Transportation Subsystem | Carts | Wheels | Assemble Wheels
Baggage handling system | Transportation Subsystem | Carts | Plateform | Construct Platform
Baggage handling system | Transportation Subsystem | Carts | Frame | Construct Frame
Baggage handling system | Transportation Subsystem | Track | Ball Bearings | Manfacture bearings
Baggage handling system | Transportation Subsystem | Track | Motor | Assemble Motor
Baggage handling system | Transportation Subsystem | Track | Computer | Assemble Computer
Baggage handling system | Transportation Subsystem | Track | Software | Operations programming
Baggage handling system | Transportation Subsystem | Track | Material? | Produce material
Baggage handling system | Transportation Subsystem | Power System | Power Supply | Determine Sources
Baggage handling system | Transportation Subsystem | Power System | Electric Grid | Design grid/layout
Baggage handling system | Transportation Subsystem | Power System | Material | Assemble components
Baggage handling system | Transportation Subsystem | Power System | Software | Program Software
Baggage handling system | Transportation Subsystem | Power System | Computer | Assemble Computer
Baggage handling system | Transportation Subsystem | Power System | Power Storage Options | Install storage options
Baggage handling system | Transportation Subsystem | Integration/Test | Software | Program Software
Baggage handling system | Transportation Subsystem | Integration/Test | Test Procedures | Design Test Procedures
Baggage handling system | Communications Subsystem | Audio Console | Speaker | Assemble speaker
Baggage handling system | Communications Subsystem | Audio Console | Amplifier | Assemble amplifier
Baggage handling system | Communications Subsystem | Audio Console | Microphone | Assemble microphone
Baggage handling system | Communications Subsystem | Walkie Talkie | Speaker | Assemble speaker
Baggage handling system | Communications Subsystem | Walkie Talkie | Amplifier | Assemble amplifier
Baggage handling system | Communications Subsystem | Walkie Talkie | Microphone | Assemble microphone
Baggage handling system | Operator Subsystem | HMI | Alert | Program Software
Baggage handling system | Operator Subsystem | HMI | Reporting System | Program Software
Baggage handling system | Operator Subsystem | HMI | GUI | Program Software
Baggage handling system | Control Subsystem | Computer | CAN BUS | Program Software
Baggage handling system | Control Subsystem | Computer | Drive Logic | Program Software
Baggage handling system | Scanning/Tracking Subsystem | Scanner | RFID | Program RFID
Baggage handling system | Scanning/Tracking Subsystem | Displays | Report | Design Reports
Baggage handling system | Scanning/Tracking Subsystem | Computer | Database | Design Database
Baggage handling system | Integration/Test | Component Assemble | Software | Program Software
Baggage handling system | Integration/Test | Component Assemble | Test Procedures | Design Test Procedures
Baggage handling system | Operations | Schedule | Calendar | Develop Calendar
Baggage handling system | Operations | Schedule | Maintenance | Determine maintenance requirements